## Sheet
Financial BU1 | [6 empty] | Financial BU2 | [6 empty] | Financial BU3
Subdiv | Budget | Expense | Usage | Revenue | Profit | Bulan | Proker | Budget | Expense | Usage | Revenue | Profit | Bulan | Proker | Budget | Expense | Usage | Revenue | Profit | Bulan
Subdiv 1 | 100 | 90 | 90% | 1000 | 400 | 31/01/2025 | Proker 1 | 80 | 75 | 93.75% | 700 | 400 | 31/01/2025 | Proker 1 | 150 | 75 | 50% | 1000 | 300 | 31/01/2025
Subdiv 2 | 100 | 80 | 80% | 1200 | 500 | 31/01/2025 | Proker 2 | 80 | 80 | 100% | 800 | 500 | 31/01/2025 | Proker 2 | 150 | 90 | 60% | 1200 | 400 | 31/01/2025
Subdiv 3 | 100 | 75 | 75% | 1300 | 800 | 31/01/2025 | Proker 3 | 80 | 90 | 112.5% | 900 | 300 | 31/01/2025 | Proker 3 | 150 | 87 | 58% | 1400 | 500 | 31/01/2025
Subdiv 4 | 100 | 98 | 98% | 1400 | 100 | 31/01/2025 | Proker 4 | 80 | 100 | 125% | 1000 | 600 | 31/01/2025 | Proker 4 | 150 | 150 | 100% | 1300 | 600 | 31/01/2025
Subdiv 5 | 100 | 100 | 100% | 1300 | 700 | 31/01/2025 | Proker 5 | 80 | 50 | 62.5% | 950 | 700 | 31/01/2025 | Proker 1 | 150 | 75 | 50% | 1000 | 300 | 28/02/2025
Subdiv 6 | 100 | 105 | 105% | 1100 | 150 | 31/01/2025 | Proker 6 | 80 | 30 | 37.5% | 850 | 350 | 31/01/2025 | Proker 2 | 150 | 90 | 60% | 1200 | 400 | 28/02/2025
Subdiv 1 | 100 | 85 | 85% | 1000 | 400 | 28/02/2025 | Proker 1 | 80 | 70 | 87.5% | 700 | 400 | 28/02/2025 | Proker 3 | 150 | 87 | 58% | 1400 | 500 | 28/02/2025
Subdiv 2 | 100 | 90 | 90% | 1200 | 500 | 28/02/2025 | Proker 2 | 80 | 90 | 112.5% | 800 | 500 | 28/02/2025 | Proker 4 | 150 | 150 | 100% | 1300 | 600 | 28/02/2025
Subdiv 3 | 100 | 100 | 100% | 1300 | 800 | 28/02/2025 | Proker 3 | 80 | 88 | 110% | 900 | 300 | 28/02/2025
Subdiv 4 | 100 | 93 | 93% | 1400 | 100 | 28/02/2025 | Proker 4 | 80 | 50 | 62.5% | 1000 | 600 | 28/02/2025
Subdiv 5 | 100 | 99 | 99% | 1300 | 700 | 28/02/2025 | Proker 5 | 80 | 30 | 37.5% | 950 | 700 | 28/02/2025
Subdiv 6 | 100 | 99 | 99% | 1100 | 150 | 28/02/2025 | Proker 6 | 80 | 78 | 97.5% | 850 | 350 | 28/02/2025
Customer & Service BU1 | [6 empty] | Customer & Service BU2 | [6 empty] | Customer & Service BU3
Produk | #of customer | Customer satisfaction | Bulan |  |  |  | Produk | #of customer | Customer satisfaction | Bulan |  |  |  | Produk | #of customer | Customer satisfaction | Bulan
PRODUK 1 | 10 | 4.5 | 31/01/2025 |  |  |  | PRODUK 1 | 9 | 4.4 | 31/01/2025 |  |  |  | PRODUK 1 | 13 | 4.2 | 31/01/2025
PRODUK 2 | 11 | 4.7 | 31/01/2025 |  |  |  | PRODUK 2 | 10 | 4.3 | 31/01/2025 |  |  |  | PRODUK 2 | 14 | 4.1 | 31/01/2025
PRODUK 3 | 12 | 4.3 | 31/01/2025 |  |  |  | PRODUK 3 | 11 | 4.5 | 31/01/2025 |  |  |  | PRODUK 3 | 13 | 4.4 | 31/01/2025
PRODUK 4 | 13 | 4.2 | 31/01/2025 |  |  |  | PRODUK 4 | 15 | 4.1 | 31/01/2025 |  |  |  | PRODUK 4 | 15 | 4.2 | 31/01/2025
PRODUK 5 | 14 | 4.1 | 31/01/2025 |  |  |  | PRODUK 5 | 17 | 4.5 | 31/01/2025 |  |  |  | PRODUK 5 | 17 | 4.4 | 31/01/2025
PRODUK 1 | 9 | 4.3 | 28/02/2025 |  |  |  | PRODUK 1 | 10 | 4.5 | 28/02/2025 |  |  |  | PRODUK 1 | 10 | 4.2 | 28/02/2025
PRODUK 2 | 8 | 4.5 | 28/02/2025 |  |  |  | PRODUK 2 | 8 | 4.7 | 28/02/2025 |  |  |  | PRODUK 2 | 13 | 4.1 | 28/02/2025
PRODUK 3 | 12 | 4.7 | 28/02/2025 |  |  |  | PRODUK 3 | 13 | 4.3 | 28/02/2025 |  |  |  | PRODUK 3 | 15 | 4.1 | 28/02/2025
PRODUK 4 | 4 | 4.8 | 28/02/2025 |  |  |  | PRODUK 4 | 7 | 4.2 | 28/02/2025 |  |  |  | PRODUK 4 | 14 | 4.4 | 28/02/2025
PRODUK 5 | 10 | 3.9 | 28/02/2025 |  |  |  | PRODUK 5 | 6 | 4.1 | 28/02/2025 |  |  |  | PRODUK 5 | 13 | 4.2 | 28/02/2025
Quality BU1 | [6 empty] | Quality BU2 | [6 empty] | Quality BU3
Subdiv | Target | Realization | Target vs Real | Velocity | Quality | Bulan | Proker | Target | Realization | Target vs Real | Velocity | Quality | Bulan | Proker | Target | Realization | Target vs Real | Velocity | Quality | Bulan
Subdiv 1 | 100 | 85 | 85% | 90% | 91% | 31/01/2025 | Proker 1 | 100 | 85 | 85% | 90% | 91% | 31/01/2025 | Proker 1 | 100 | 85 | 85% | 90% | 86% | 31/01/2025
Subdiv 2 | 100 | 95 | 95% | 85% | 86% | 31/01/2025 | Proker 2 | 100 | 95 | 95% | 85% | 86% | 31/01/2025 | Proker 2 | 100 | 95 | 95% | 85% | 77% | 31/01/2025
Subdiv 3 | 100 | 90 | 90% | 76% | 77% | 31/01/2025 | Proker 3 | 100 | 90 | 90% | 76% | 77% | 31/01/2025 | Proker 3 | 100 | 90 | 90% | 76% | 99% | 31/01/2025
Subdiv 4 | 100 | 89 | 89% | 100% | 99% | 31/01/2025 | Proker 4 | 100 | 89 | 89% | 100% | 99% | 31/01/2025 | Proker 4 | 100 | 89 | 89% | 100% | 85% | 31/01/2025
Subdiv 5 | 100 | 98 | 98% | 120% | 85% | 31/01/2025 | Proker 5 | 100 | 98 | 98% | 120% | 85% | 31/01/2025 | Proker 1 | 100 | 87 | 87% | 91% | 90% | 28/02/2025
Subdiv 6 | 100 | 100 | 100% | 75% | 100% | 31/01/2025 | Proker 6 | 100 | 100 | 100% | 75% | 100% | 31/01/2025 | Proker 2 | 100 | 94 | 94% | 84% | 87% | 28/02/2025
Subdiv 1 | 100 | 87 | 87% | 91% | 90% | 28/02/2025 | Proker 1 | 100 | 87 | 87% | 91% | 90% | 28/02/2025 | Proker 3 | 100 | 93 | 93% | 77% | 76% | 28/02/2025
Subdiv 2 | 100 | 94 | 94% | 84% | 87% | 28/02/2025 | Proker 2 | 100 | 94 | 94% | 84% | 87% | 28/02/2025 | Proker 4 | 100 | 91 | 91% | 99% | 100% | 28/02/2025
Subdiv 3 | 100 | 93 | 93% | 77% | 76% | 28/02/2025 | Proker 3 | 100 | 93 | 93% | 77% | 76% | 28/02/2025
Subdiv 4 | 100 | 91 | 91% | 99% | 100% | 28/02/2025 | Proker 4 | 100 | 91 | 91% | 99% | 100% | 28/02/2025
Subdiv 5 | 100 | 100 | 100% | 99% | 84% | 28/02/2025 | Proker 5 | 100 | 100 | 100% | 99% | 84% | 28/02/2025
Subdiv 6 | 100 | 95 | 95% | 74% | 99% | 28/02/2025 | Proker 6 | 100 | 95 | 95% | 74% | 99% | 28/02/2025
Employee BU1 | [6 empty] | Employee BU2 | [6 empty] | Employee BU3
Subdiv | Current MP | Needed MP | Competency | Turnover ratio | Bulan |  | Proker | Current MP | Needed MP | Competency | Turnover ratio | Bulan |  | Proker | Current MP | Needed MP | Competency | Turnover ratio | Bulan
Subdiv 1 | 48 | 50 | 90% | 5% | 31/01/2025 |  | Proker 1 | 48 | 50 | 90% | 5% | 31/01/2025 |  | Proker 1 | 48 | 50 | 90% | 5% | 31/01/2025
Subdiv 2 | 35 | 35 | 85% | 3% | 31/01/2025 |  | Proker 2 | 35 | 35 | 85% | 3% | 31/01/2025 |  | Proker 2 | 35 | 35 | 85% | 3% | 31/01/2025
Subdiv 3 | 20 | 21 | 100% | 2% | 31/01/2025 |  | Proker 3 | 20 | 21 | 100% | 2% | 31/01/2025 |  | Proker 3 | 20 | 21 | 100% | 2% | 31/01/2025
Subdiv 4 | 40 | 40 | 100% | 5% | 31/01/2025 |  | Proker 4 | 40 | 40 | 100% | 5% | 31/01/2025 |  | Proker 4 | 40 | 40 | 100% | 5% | 31/01/2025
Subdiv 5 | 25 | 35 | 75% | 10% | 31/01/2025 |  | Proker 5 | 25 | 35 | 75% | 10% | 31/01/2025 |  | Proker 1 | 47 | 50 | 88% | 7% | 28/02/2025
Subdiv 6 | 20 | 20 | 100% | 7% | 31/01/2025 |  | Proker 6 | 20 | 20 | 100% | 7% | 31/01/2025 |  | Proker 2 | 34 | 35 | 87% | 5% | 28/02/2025
Subdiv 1 | 47 | 50 | 88% | 7% | 28/02/2025 |  | Proker 1 | 47 | 50 | 88% | 7% | 28/02/2025 |  | Proker 3 | 21 | 21 | 100% | 2% | 28/02/2025
Subdiv 2 | 34 | 35 | 87% | 5% | 28/02/2025 |  | Proker 2 | 34 | 35 | 87% | 5% | 28/02/2025 |  | Proker 4 | 38 | 40 | 98% | 8% | 28/02/2025
Subdiv 3 | 21 | 21 | 100% | 2% | 28/02/2025 |  | Proker 3 | 21 | 21 | 100% | 2% | 28/02/2025
Subdiv 4 | 38 | 40 | 98% | 8% | 28/02/2025 |  | Proker 4 | 38 | 40 | 98% | 8% | 28/02/2025
Subdiv 5 | 28 | 35 | 89% | 5% | 28/02/2025 |  | Proker 5 | 28 | 35 | 89% | 5% | 28/02/2025
Subdiv 6 | 20 | 20 | 100% | 3% | 28/02/2025 |  | Proker 6 | 20 | 20 | 100% | 3% | 28/02/2025
Financial overall BU | [6 empty] | Employee_overall_BU
BU | Budget | Expense | Usage | Revenue | Profit | Bulan | BU | Current MP | Needed MP | Competency | Turnover ratio | Bulan
BU1 | 600 | 548 | 91.33% | 7300 | 2650 | 31/01/2025 | BU1 | 188 | 201 | 91.67% | 5.333%
BU2 | 480 | 425 | 88.54% | 5200 | 2850 | 31/01/2025 | BU2 | 188 | 201 | 91.67% | 5.333%
BU3 | 600 | 402 | 67% | 4900 | 1800 | 31/01/2025 | BU3 | 143 | 146 | 93.75% | 3.75%
BU1 | 600 | 566 | 94.33% | 7300 | 2650 | 28/02/2025 | BU1 | 188 | 201 | 93.67% | 5%
BU2 | 480 | 406 | 84.58% | 5200 | 2850 | 28/02/2025 | BU2 | 188 | 201 | 93.67% | 5%
BU3 | 600 | 402 | 101% | 402 | 402 | 28/02/2025 | BU3 | 140 | 146 | 93.25% | 5.5%
Customer_n_Service_BU
BU | #of customer | Customer satisfaction | Bulan
BU1 | 60 | 4.36 | 31/01/2025
BU2 | 62 | 4.36 | 31/01/2025
BU3 | 72 | 4.26 | 31/01/2025
BU1 | 43 | 4.44 | 28/02/2025
BU2 | 44 | 4.36 | 28/02/2025
BU3 | 65 | 4.23 | 28/02/2025
Quality_overall
BU | Target | Realization | Target vs Real | Velocity | Quality | Bulan
BU1 | 600 | 557 | 92.83% | 91% | 89.67% | 31/01/2025
BU2 | 600 | 557 | 92.83% | 91% | 89.67% | 31/01/2025
BU3 | 400 | 359 | 89.75% | 87.75% | 86.75% | 31/01/2025
BU1 | 600 | 560 | 93.33% | 87.33% | 89.33% | 28/02/2025
BU2 | 600 | 560 | 93.33% | 87.33% | 89.33% | 28/02/2025
BU3 | 400 | 365 | 91.25% | 87.75% | 88.25% | 28/02/2025

## Sheet1
Financial
Subdiv BU1 | Budget BU1 | Expense BU1 | Usage BU1 | Revenue BU1 | Profit BU1 | Proker BU1 | Budget BU2 | Expense BU2 | Usage BU2 | Revenue BU2 | Profit BU2 | Bulan BU12 | Proker BU3 | Budget BU3 | Expense BU3 | Usage BU3 | Revenue BU3 | Profit BU3 | Bulan
Subdiv 1 | 100 | 90 | 90% | 1000 | 400 | Proker 1 | 80 | 75 | 93.75% | 700 | 400 | 31/01/2025 | Proker 1 | 150 | 75 | 50% | 1000 | 300 | 31/01/2025
Subdiv 2 | 100 | 80 | 80% | 1200 | 500 | Proker 2 | 80 | 80 | 100% | 800 | 500 | 31/01/2025 | Proker 2 | 150 | 90 | 60% | 1200 | 400 | 31/01/2025
Subdiv 3 | 100 | 75 | 75% | 1300 | 800 | Proker 3 | 80 | 90 | 112.5% | 900 | 300 | 31/01/2025 | Proker 3 | 150 | 87 | 58% | 1400 | 500 | 31/01/2025
Subdiv 4 | 100 | 98 | 98% | 1400 | 100 | Proker 4 | 80 | 100 | 125% | 1000 | 600 | 31/01/2025 | Proker 4 | 150 | 150 | 100% | 1300 | 600 | 31/01/2025
Subdiv 5 | 100 | 100 | 100% | 1300 | 700 | Proker 5 | 80 | 50 | 62.5% | 950 | 700 | 31/01/2025 | Nol | [5 empty] | 31/01/2025
Subdiv 6 | 100 | 105 | 105% | 1100 | 150 | Proker 6 | 80 | 30 | 37.5% | 850 | 350 | 31/01/2025 | Nol | [5 empty] | 31/01/2025
Subdiv 1 | 100 | 85 | 85% | 1000 | 400 | Proker 1 | 80 | 70 | 87.5% | 700 | 400 | 28/02/2025 | Proker 1 | 150 | 75 | 50% | 1000 | 300 | 28/02/2025
Subdiv 2 | 100 | 90 | 90% | 1200 | 500 | Proker 2 | 80 | 90 | 112.5% | 800 | 500 | 28/02/2025 | Proker 2 | 150 | 90 | 60% | 1200 | 400 | 28/02/2025
Subdiv 3 | 100 | 100 | 100% | 1300 | 800 | Proker 3 | 80 | 88 | 110% | 900 | 300 | 28/02/2025 | Proker 3 | 150 | 87 | 58% | 1400 | 500 | 28/02/2025
Subdiv 4 | 100 | 93 | 93% | 1400 | 100 | Proker 4 | 80 | 50 | 62.5% | 1000 | 600 | 28/02/2025 | Proker 4 | 150 | 150 | 100% | 1300 | 600 | 28/02/2025
Subdiv 5 | 100 | 99 | 99% | 1300 | 700 | Proker 5 | 80 | 30 | 37.5% | 950 | 700 | 28/02/2025 | Nol | [5 empty] | 28/02/2025
Subdiv 6 | 100 | 99 | 99% | 1100 | 150 | Proker 6 | 80 | 78 | 97.5% | 850 | 350 | 28/02/2025 | Nol | [5 empty] | 28/02/2025
Customer_n_service
Produk BU1 | #of customer BU1 | Customer satisfaction BU1 | Produk BU2 | #of customer BU2 | Customer satisfaction BU2 | Produk BU3 | #of customer BU3 | Customer satisfaction BU3 | Bulan
PRODUK 1 | 10 | 4.5 | PRODUK 1 | 9 | 4.4 | PRODUK 1 | 13 | 4.2 | 31/01/2025
PRODUK 2 | 11 | 4.7 | PRODUK 2 | 10 | 4.3 | PRODUK 2 | 14 | 4.1 | 31/01/2025
PRODUK 3 | 12 | 4.3 | PRODUK 3 | 11 | 4.5 | PRODUK 3 | 13 | 4.4 | 31/01/2025
PRODUK 4 | 13 | 4.2 | PRODUK 4 | 15 | 4.1 | PRODUK 4 | 15 | 4.2 | 31/01/2025
PRODUK 5 | 14 | 4.1 | PRODUK 5 | 17 | 4.5 | PRODUK 5 | 17 | 4.4 | 31/01/2025
PRODUK 1 | 9 | 4.3 | PRODUK 1 | 10 | 4.5 | PRODUK 1 | 10 | 4.2 | 28/02/2025
PRODUK 2 | 8 | 4.5 | PRODUK 2 | 8 | 4.7 | PRODUK 2 | 13 | 4.1 | 28/02/2025
PRODUK 3 | 12 | 4.7 | PRODUK 3 | 13 | 4.3 | PRODUK 3 | 15 | 4.1 | 28/02/2025
PRODUK 4 | 4 | 4.8 | PRODUK 4 | 7 | 4.2 | PRODUK 4 | 14 | 4.4 | 28/02/2025
PRODUK 5 | 10 | 3.9 | PRODUK 5 | 6 | 4.1 | PRODUK 5 | 13 | 4.2 | 28/02/2025
Quality
Subdiv BU1 | Target BU1 | Realization BU1 | Target vs Real BU1 | Velocity BU1 | Quality BU1 | Proker BU2 | Target BU2 | Realization BU2 | Target vs Real BU2 | Velocity BU2 | Quality BU2 | Proker BU3 | Target BU3 | Realization BU3 | Target vs Real BU3 | Velocity BU3 | Quality BU3 | Bulan
Subdiv 1 | 100 | 85 | 85% | 90% | 91% | Proker 1 | 100 | 85 | 85% | 90% | 91% | Proker 1 | 100 | 85 | 85% | 90% | 86% | 31/01/2025
Subdiv 2 | 100 | 95 | 95% | 85% | 86% | Proker 2 | 100 | 95 | 95% | 85% | 86% | Proker 2 | 100 | 95 | 95% | 85% | 77% | 31/01/2025
Subdiv 3 | 100 | 90 | 90% | 76% | 77% | Proker 3 | 100 | 90 | 90% | 76% | 77% | Proker 3 | 100 | 90 | 90% | 76% | 99% | 31/01/2025
Subdiv 4 | 100 | 89 | 89% | 100% | 99% | Proker 4 | 100 | 89 | 89% | 100% | 99% | Proker 4 | 100 | 89 | 89% | 100% | 85% | 31/01/2025
Subdiv 5 | 100 | 98 | 98% | 120% | 85% | Proker 5 | 100 | 98 | 98% | 120% | 85% | Nol | [5 empty] | 31/01/2025
Subdiv 6 | 100 | 100 | 100% | 75% | 100% | Proker 6 | 100 | 100 | 100% | 75% | 100% | Nol | [5 empty] | 31/01/2025
Subdiv 1 | 100 | 87 | 87% | 91% | 90% | Proker 1 | 100 | 87 | 87% | 91% | 90% | Proker 1 | 100 | 87 | 87% | 91% | 90% | 28/02/2025
Subdiv 2 | 100 | 94 | 94% | 84% | 87% | Proker 2 | 100 | 94 | 94% | 84% | 87% | Proker 2 | 100 | 94 | 94% | 84% | 87% | 28/02/2025
Subdiv 3 | 100 | 93 | 93% | 77% | 76% | Proker 3 | 100 | 93 | 93% | 77% | 76% | Proker 3 | 100 | 93 | 93% | 77% | 76% | 28/02/2025
Subdiv 4 | 100 | 91 | 91% | 99% | 100% | Proker 4 | 100 | 91 | 91% | 99% | 100% | Proker 4 | 100 | 91 | 91% | 99% | 100% | 28/02/2025
Subdiv 5 | 100 | 100 | 100% | 99% | 84% | Proker 5 | 100 | 100 | 100% | 99% | 84% | Nol | [5 empty] | 28/02/2025
Subdiv 6 | 100 | 95 | 95% | 74% | 99% | Proker 6 | 100 | 95 | 95% | 74% | 99% | Nol | [5 empty] | 28/02/2025
Employee
Subdiv BU1 | Current MP BU1 | Needed MP BU1 | Competency BU1 | Turnover ratio BU1 | Proker BU2 | Current MP BU2 | Needed MP BU2 | Competency BU2 | Turnover ratio BU2 | Proker BU3 | Current MP BU3 | Needed MP BU3 | Competency BU3 | Turnover ratio BU3 | Bulan BU3
Subdiv 1 | 48 | 50 | 90% | 5% | Proker 1 | 48 | 50 | 90% | 5% | Proker 1 | 48 | 50 | 90% | 5% | 31/01/2025
Subdiv 2 | 35 | 35 | 85% | 3% | Proker 2 | 35 | 35 | 85% | 3% | Proker 2 | 35 | 35 | 85% | 3% | 31/01/2025
Subdiv 3 | 20 | 21 | 100% | 2% | Proker 3 | 20 | 21 | 100% | 2% | Proker 3 | 20 | 21 | 100% | 2% | 31/01/2025
Subdiv 4 | 40 | 40 | 100% | 5% | Proker 4 | 40 | 40 | 100% | 5% | Proker 4 | 40 | 40 | 100% | 5% | 31/01/2025
Subdiv 5 | 25 | 35 | 75% | 10% | Proker 5 | 25 | 35 | 75% | 10% | Nol |  |  |  |  | 31/01/2025
Subdiv 6 | 20 | 20 | 100% | 7% | Proker 6 | 20 | 20 | 100% | 7% | Nol |  |  |  |  | 31/01/2025
Subdiv 1 | 47 | 50 | 88% | 7% | Proker 1 | 47 | 50 | 88% | 7% | Proker 1 | 47 | 50 | 88% | 7% | 28/02/2025
Subdiv 2 | 34 | 35 | 87% | 5% | Proker 2 | 34 | 35 | 87% | 5% | Proker 2 | 34 | 35 | 87% | 5% | 28/02/2025
Subdiv 3 | 21 | 21 | 100% | 2% | Proker 3 | 21 | 21 | 100% | 2% | Proker 3 | 21 | 21 | 100% | 2% | 28/02/2025
Subdiv 4 | 38 | 40 | 98% | 8% | Proker 4 | 38 | 40 | 98% | 8% | Proker 4 | 38 | 40 | 98% | 8% | 28/02/2025
Subdiv 5 | 28 | 35 | 89% | 5% | Proker 5 | 28 | 35 | 89% | 5% | Nol |  |  |  |  | 28/02/2025
Subdiv 6 | 20 | 20 | 100% | 3% | Proker 6 | 20 | 20 | 100% | 3% | Nol |  |  |  |  | 28/02/2025
Overall_bu
BU | Budget Finance | Expense Finance | Usage Finance | Revenue Finance | Profit Finance | #of customer Customer | Customer satisfaction Customer | Target Quality | Realization Quality | Target vs Real Quality | Velocity Quality | Quality | Current MP Employee | Needed MP Employee | Competency Employee | Turnover ratio Employee | Bulan Quality
BU1 | 600 | 548 | 91.33% | 7300 | 2650 | 60 | 4.36 | 600 | 557 | 92.83% | 91% | 89.67% | 188 | 201 | 91.67% | 5.333% | 31/01/2025
BU2 | 480 | 425 | 88.54% | 5200 | 2850 | 62 | 4.36 | 600 | 557 | 92.83% | 91% | 89.67% | 188 | 201 | 91.67% | 5.333% | 31/01/2025
BU3 | 600 | 402 | 67% | 4900 | 1800 | 72 | 4.26 | 400 | 359 | 89.75% | 87.75% | 86.75% | 143 | 146 | 93.75% | 3.75% | 31/01/2025
Total Jan | 1680 | 1375 | 82.29% | 17400 | 7300 | 194 | 4.3267 | 1600 | 1473 | 91.81% | 89.92% | 88.69% | 519 | 548 | 92.36% | 4.806% | 31/01/2025
BU1 | 600 | 566 | 94.33% | 7300 | 2650 | 43 | 4.44 | 600 | 560 | 93.33% | 87.33% | 89.33% | 188 | 201 | 93.67% | 5% | 28/02/2025
BU2 | 480 | 406 | 84.58% | 5200 | 2850 | 44 | 4.36 | 600 | 560 | 93.33% | 87.33% | 89.33% | 188 | 201 | 93.67% | 5% | 28/02/2025
BU3 | 600 | 402 | 101% | 402 | 402 | 65 | 4.23 | 400 | 365 | 91.25% | 87.75% | 88.25% | 140 | 146 | 93.25% | 5.5% | 28/02/2025
Total Feb | 1680 | 1374 | 93.31% | 12902 | 5902 | 152 | 4.3433 | 1600 | 1485 | 92.64% | 87.47% | 88.97% | 516 | 548 | 93.53% | 5.167% | 28/02/2025

## Sheet2BU1
Financial BU1
Perspective | Subdiv | Budget | Expense | Usage | Revenue | Profit | Bulan | Produk | #of customer | Customer satisfaction | Target | Realization | Target vs Real | Velocity | Quality | Current MP | Needed MP | Competency | Turnover ratio
Financial | Subdiv 1 | 100 | 90 | 90% | 1000 | 400 | 31/01/2025
Financial | Subdiv 2 | 100 | 80 | 80% | 1200 | 500 | 31/01/2025
Financial | Subdiv 3 | 100 | 75 | 75% | 1300 | 800 | 31/01/2025
Financial | Subdiv 4 | 100 | 98 | 98% | 1400 | 100 | 31/01/2025
Financial | Subdiv 5 | 100 | 100 | 100% | 1300 | 700 | 31/01/2025
Financial | Subdiv 6 | 100 | 105 | 105% | 1100 | 150 | 31/01/2025
Financial | Subdiv 1 | 100 | 85 | 85% | 1000 | 400 | 28/02/2025
Financial | Subdiv 2 | 100 | 90 | 90% | 1200 | 500 | 28/02/2025
Financial | Subdiv 3 | 100 | 100 | 100% | 1300 | 800 | 28/02/2025
Financial | Subdiv 4 | 100 | 93 | 93% | 1400 | 100 | 28/02/2025
Financial | Subdiv 5 | 100 | 99 | 99% | 1300 | 700 | 28/02/2025
Financial | Subdiv 6 | 100 | 99 | 99% | 1100 | 150 | 28/02/2025
Customer n Service | [6 empty] | 31/01/2025 | PRODUK 1 | 10 | 4.5
Customer n Service | [6 empty] | 31/01/2025 | PRODUK 2 | 11 | 4.7
Customer n Service | [6 empty] | 31/01/2025 | PRODUK 3 | 12 | 4.3
Customer n Service | [6 empty] | 31/01/2025 | PRODUK 4 | 13 | 4.2
Customer n Service | [6 empty] | 31/01/2025 | PRODUK 5 | 14 | 4.1
Customer n Service | [6 empty] | 28/02/2025 | PRODUK 1 | 9 | 4.3
Customer n Service | [6 empty] | 28/02/2025 | PRODUK 2 | 8 | 4.5
Customer n Service | [6 empty] | 28/02/2025 | PRODUK 3 | 12 | 4.7
Customer n Service | [6 empty] | 28/02/2025 | PRODUK 4 | 4 | 4.8
Customer n Service | [6 empty] | 28/02/2025 | PRODUK 5 | 10 | 3.9
Quality | Subdiv 1 | [5 empty] | 31/01/2025 |  |  |  | 100 | 85 | 85% | 90% | 91%
Quality | Subdiv 2 | [5 empty] | 31/01/2025 |  |  |  | 100 | 95 | 95% | 85% | 86%
Quality | Subdiv 3 | [5 empty] | 31/01/2025 |  |  |  | 100 | 90 | 90% | 76% | 77%
Quality | Subdiv 4 | [5 empty] | 31/01/2025 |  |  |  | 100 | 89 | 89% | 100% | 99%
Quality | Subdiv 5 | [5 empty] | 31/01/2025 |  |  |  | 100 | 98 | 98% | 120% | 85%
Quality | Subdiv 6 | [5 empty] | 31/01/2025 |  |  |  | 100 | 100 | 100% | 75% | 100%
Quality | Subdiv 1 | [5 empty] | 28/02/2025 |  |  |  | 100 | 87 | 87% | 91% | 90%
Quality | Subdiv 2 | [5 empty] | 28/02/2025 |  |  |  | 100 | 94 | 94% | 84% | 87%
Quality | Subdiv 3 | [5 empty] | 28/02/2025 |  |  |  | 100 | 93 | 93% | 77% | 76%
Quality | Subdiv 4 | [5 empty] | 28/02/2025 |  |  |  | 100 | 91 | 91% | 99% | 100%
Quality | Subdiv 5 | [5 empty] | 28/02/2025 |  |  |  | 100 | 100 | 100% | 99% | 84%
Quality | Subdiv 6 | [5 empty] | 28/02/2025 |  |  |  | 100 | 95 | 95% | 74% | 99%
Employee | Subdiv 1 | [5 empty] | 31/01/2025 | [8 empty] | 48 | 50 | 90% | 5%
Employee | Subdiv 2 | [5 empty] | 31/01/2025 | [8 empty] | 35 | 35 | 85% | 3%
Employee | Subdiv 3 | [5 empty] | 31/01/2025 | [8 empty] | 20 | 21 | 100% | 2%
Employee | Subdiv 4 | [5 empty] | 31/01/2025 | [8 empty] | 40 | 40 | 100% | 5%
Employee | Subdiv 5 | [5 empty] | 31/01/2025 | [8 empty] | 25 | 35 | 75% | 10%
Employee | Subdiv 6 | [5 empty] | 31/01/2025 | [8 empty] | 20 | 20 | 100% | 7%
Employee | Subdiv 1 | [5 empty] | 28/02/2025 | [8 empty] | 47 | 50 | 88% | 7%
Employee | Subdiv 2 | [5 empty] | 28/02/2025 | [8 empty] | 34 | 35 | 87% | 5%
Employee | Subdiv 3 | [5 empty] | 28/02/2025 | [8 empty] | 21 | 21 | 100% | 2%
Employee | Subdiv 4 | [5 empty] | 28/02/2025 | [8 empty] | 38 | 40 | 98% | 8%
Employee | Subdiv 5 | [5 empty] | 28/02/2025 | [8 empty] | 28 | 35 | 89% | 5%
Employee | Subdiv 6 | [5 empty] | 28/02/2025 | [8 empty] | 20 | 20 | 100% | 3%

## Progress (hidden)
TASK | PIC | Prerequisite | Definition of Done | START | END | Status | Summary
ACE New Expansion | [6 empty] | Started, As Scheduled | 22 | 20 | 20 | 3 | 2 | 0
Determine industry profile requirement | LLE | BMC, PASTLE, Porter 5 Forces, SWOT untuk Recruitment, Training dan BPO | Tersedianya profile industry dari target market yang akan dipenetrasi. Money: average budget, growth, revenue Authority: decision maker, influencer, entry point Needs: what, quantity, why, when Deliverable: - Report Industry Profile (Desk Research) - Validasi by sales terkait desk research yang dilakukan Approver: Scope pekerjaan -> DIC | 2025-02-19 | 2025-04-25 | Started, As Scheduled | Not Started, As Scheduled | 3 | 3
Develop new training program development SOP (feasibility study) - CONFINS | RAG | Objective dan Materi Training CONFINS | Tersedianya SOP sebelum, saat, setelah pelaksanaan untuk menjalankan training program CONFINS serta feasibility study-nya. Deliverable: Document SOP Training ACE x CONFINS Approver: BU Head + DIC | 2025-02-18 | 2025-03-20 | Started, As Scheduled | Not Started, Late | 0 | 2
Develop new training program development SOP (feasibility study) - University | SDP | Objective dan Hasil Desk Research Training di University | Tersedianya SOP sebelum, saat, setelah pelaksanaan untuk menjalankan training program University serta feasibility study-nya. Deliverable: Document SOP Training di University Approver: BU Head + DIC | 2025-02-18 | 2025-03-14 | Started, As Scheduled | Finished | 0 | 0
Identify new BPO solutions to be researched | RSE | List Target Industry (desk research) dari WBS 1.1 List Pertanyaan Menggali Informasi | Tersedianya solusi BPO yang siap untuk dijual ke market tujuan beserta dengan deck sederhana (masalah yang akan dihandle dan benefit solusi). Deliverable: Deck Solusi BPO (masalah industry, solusi product, daftar kompetitor Approver: BU Head + DIC | 2025-02-19 | 31/04/2025 | Started, As Scheduled | Total | 25
Implement industry knowledge training program | SDP | Target Industry yang telah di sepakati di Planning Cycle 2025 List materi pelatihan Mendapatkan expert di 2 industry | Terlaksananya training tentang industry yang menjadi target market. (Banking & University) Deliverable: Training Target Industry Knowledge Banking -> Winoto (IT HC BCA) Univesity -> DAW Approver: BU Head + DIC | 2025-02-18 | 2025-03-20 | Started, As Scheduled
ACE Brand & Market Elevate
Develop partnership package (individual and organization) | MTT | 1. Skema kerjasama eksisting 2. Skema kerjasama best practice | Tersedianya skema kerja sama pemasaran dengan individu dan juga organisasi untuk masing-masing produk. | 2025-02-03 | 2025-02-21 | Started, As Scheduled
Website revamp | ELA | 1. Vendor website development 2. Tersedianya logo terbaru untuk go live 3. Ekspektasi revamp 4. Budget untuk revamp | Tersedianya website dengan versi terbaru yang lebih informatif, user friendly, memenuhi ekspektasi dan kebutuhan ACE. | 2025-02-17 | 2025-03-07 | Started, As Scheduled
Develop socmed program | ELA | 1. Akun sosial media (IG, Tiktok, LinkedIn, Youtube) | Tersedianya social media dan content planning default setiap bulannya dan content calendar untuk bulan Maret. | 2025-02-03 | 2025-02-28 | Started, As Scheduled
ACE Process Excellence
Develop SOP for outsource management | MTT | Template SOP informasi proses existing | Tersedianya SOP pengelolaan karyawan outsource yang akan habis masa kontraknya. Deliverable: SOP Document Approver: BU Head (DDD) | 2025-02-19 | 2025-03-20 | Started, As Scheduled
Develop talent inventory data maintenance SOP | MTT | Template SOP informasi proses existing | Tersedianya SOP untuk maintain/manage database talent. Deliverable: SOP Document Approver: BU Head (DDD) | 2025-02-19 | 2025-03-20 | Started, As Scheduled
Review and improve channel incentive scheme | YOC | Skema perhitungan existing Target Improvement | Tersedianya skema insentif untuk mitra rekrutmen channel/organisasi. Deliverable: Dokumen Skema insentif Mitra Approver: BU Head (DDD) | 2025-02-19 | 2025-03-10 | Started, As Scheduled
Review and improve individual incentive scheme | YOC | Skema perhitungan existing Target Improvement | Tersedianya skema insentif untuk mitra rekrutmen individu. Deliverable: Dokumen Skema insentif Mitra Approver: BU Head (DDD) | 2025-02-19 | 2025-03-10 | Started, As Scheduled
Implement engagement event model for recruitment partners | DAN | List Schedule Mitra | Terlaksana kegiatan engagement dengan mitra rekrutmen. | 2025-02-19 | 2025-03-10 | Started, As Scheduled
Review and improve trainer recruitment SOP | MJU | Template SOP informasi proses existing | Tersedianya SOP untuk merekrut trainer. Deliverable: SOP Document Approver: BU Head (DDD) | 2025-02-19 | 2025-03-20 | Started, As Scheduled
Review and improve training SOP | SDP | Template SOP informasi proses existing | Tersedianya SOP dan panduan proses pelaksaan training. Deliverable: SOP Document Approver: BU Head (DDD) | 2025-02-19 | 2025-03-20 | Started, As Scheduled
Develop competency matrix for outsource talent | HMU | Performance appraisal karyawan outsource Kriteria High Quality Talent | Tersedianya matrix competency high quality talent. | 2025-02-19 | 2025-03-21 | Started, As Scheduled
Design and develop individual outsource talent development program | YOC | 3.8 Competency matrix for outsource talent | Tersedia rencana pengembangan karyawan outsource yang masuk kategori high quality talent. | 2025-02-19 | 2025-03-21 | Started, As Scheduled
Implement R&C program for employee | SDP | Skema best practice dalam melakukan R&C | Tersedianya skema reward & consequences untuk karyawan internal ACE. | 2025-02-19 | 2025-03-20 | Started, As Scheduled
Relevant training for employee | ADF | Materi Training yg akan diikuti List Karyawan yang perlu di training Jadwal training | Terlaksananya training untuk karyawan internal ACE. | 2025-02-19 | 2025-03-20 | Started, As Scheduled
ACE Digital Enablement
Develop sales and marketing tools (catalogue and testimonial) | DAN | - Data talent inventory sudah tervalidasi. - List sasaran user/client untuk diminta testimonial | Tersedianya sales deck versi terbaru dengan katalog posisi talent IT yang dimiliki saat ini di database dan testimoni dari user/client terhadap karyawan outsource ACE. Deliverable: Catalog Sales Deck Approval: DDD | 2025-03-14 | 2025-03-28 | Not Started, As Scheduled
Explore digital marketing for recruitment | ELA | - 2.2 Website ACE terbaru go live. - ekspektasi form apply | Tersedianya data riset ( harga ads, ads yang dipakai oleh competitor, reach masing masing ads or platform, dan data lain) dan dapat digunakan sebagai informasi untuk decision making, serta tersedianya platform/form untuk apply. Deliverable: Form Apply Job, Report Riset Platform dan rekomendasi Approval: DDD | 2025-03-07 | 2025-03-20 | Not Started, As Scheduled
Develop event booth for candidates recruitment | DAN | - Hasil Desk Research - ekspektasi hasil flyer, banner, booth - 2.2 Website ACE terbaru go live | Tersedianya supporting tools yang akan digunakan untuk proses event (form apply, booth, banner, flyer) Deliverable: QR Code, Booth, Flyer dan Banner template, Approval: DDD | 2025-03-07 | 2025-03-28 | Not Started, As Scheduled
Develop talent inventory management tools | AFA | Requirement ATS | Tersedianya roadmap development ATS. Deliverable: feature yang ada roadmap ATS Approval: DDD | 2025-01-02 | 2025-03-18 | Started, As Scheduled
AI automation for Talent Recruitment & Management | RAY | - list process all product - vendor untuk handle AI - proposal vendor - budget vendor - ekspektasi dampak penggunaan AI | Terimplementasi AI pada internal proses talent recruitment & management. Deliverable: Project Implementation Monitoring, report before after setelah AI Approval: DDD | 2025-02-18 | 2025-03-28 | Started, As Scheduled
Develop task management application for recruitment partners | DSW | 4.4 talent inventory management tools sudah ready 3.3 Skema Incentive Mitra 3.4 Skema Incentive Channel | Revamp aplikasi mitra dapat memfasilitasi baik ( pelamar, mitra rekrutmen individual dan channel). Deliverable: Website Mitra & Channels, feature baru di website Approval: DDD | 2025-02-18 | 2025-03-28 | Started, As Scheduled
Not Started, As Scheduled
|  |  | Develop sales and marketing tools (catalogue and testimonial) | 2025-03-14 | 2025-03-28
|  |  | Explore digital marketing for recruitment | 2025-03-07 | 2025-03-20
|  |  | Develop event booth for candidates recruitment | 2025-03-07 | 2025-03-28
Not Started, Late
|  |  | Develop talent inventory management tools | Thu 02/01/25 | Mon 10/03/25
|  |  | AI automation for Talent Recruitment & Management | Tue 18/02/25 | Fri 28/03/25
Started, As Scheduled
|  |  | Determine industry profile requirement | 2025-02-19 | 2025-04-25
|  |  | Develop new training program development SOP (feasibility study) - CONFINS | 2025-02-18 | 2025-03-20
|  |  | Develop new training program development SOP (feasibility study) - University | 2025-02-18 | 2025-03-14
|  |  | Identify new BPO solutions to be researched | 2025-02-19 | 31/04/2025
|  |  | Implement industry knowledge training program | 2025-02-18 | 2025-03-20
|  |  | Develop partnership package (individual and organization) | 2025-02-03 | 2025-02-21
|  |  | Website revamp | 2025-02-17 | 2025-03-07
|  |  | Develop socmed program | 2025-02-03 | 2025-02-28
|  |  | Develop SOP for outsource management | 2025-02-19 | 2025-03-20
|  |  | Develop talent inventory data maintenance SOP | 2025-02-19 | 2025-03-20
|  |  | Review and improve channel incentive scheme | 2025-02-19 | 2025-03-10
|  |  | Review and improve individual incentive scheme | 2025-02-19 | 2025-03-10
|  |  | Implement engagement event model for recruitment partners | 2025-02-19 | 2025-03-10
|  |  | Review and improve trainer recruitment SOP | 2025-02-19 | 2025-03-20
|  |  | Review and improve training SOP | 2025-02-19 | 2025-03-20
|  |  | Develop competency matrix for outsource talent | 2025-02-19 | 2025-03-21
|  |  | Design and develop individual outsource talent development program | 2025-02-19 | 2025-03-21
|  |  | Implement R&C program for employee | 2025-02-19 | 2025-03-20
|  |  | Relevant training for employee | 2025-02-19 | 2025-03-20
|  |  | Develop task management application for recruitment partners | 2025-02-18 | 2025-03-28

## GanttChart (bup070325) (hidden)
| Project Start Date : | [8 empty] | Display Week
| 2025-01-02 | [8 empty] | 6 |  | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15
[12 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07
 | time axis 2025-02-03 to 2025-04-13
WBS | TASK | PIC | Prerequisite | Definition of Done | START | END | DAYS | % DONE | WORK DAYS | ACTUAL END | DELAY | time axis 2025-02-03 to 2025-04-13
1 | ACE New Expansion | MEG |  |  | 2025-02-18 | 2025-04-30 | 72 | 0% | #REF! |  | -
1.1 | Determine industry profile requirement | LLE | BMC, PASTLE, Porter 5 Forces, SWOT untuk Recruitment, Training dan BPO | Tersedianya profile industry dari target market yang akan dipenetrasi. Money: average budget, growth, revenue Authority: decision maker, influencer, entry point Needs: what, quantity, why, when Deliverable: - Report Industry Profile (Desk Research) - Validasi by sales terkait desk research yang dilakukan Approver: Scope pekerjaan -> DIC | 2025-02-19 | 2025-04-25 | 66 | 0% | #REF! |  | -
1.2 | Develop new training program development SOP (feasibility study) - CONFINS | RAG | Objective dan Materi Training CONFINS | Tersedianya SOP sebelum, saat, setelah pelaksanaan untuk menjalankan training program CONFINS serta feasibility study-nya. Deliverable: Document SOP Training ACE x CONFINS Approver: BU Head + DIC | 2025-02-18 | 2025-03-20 | 31 | 0% | #REF! |  | -
1.3 | Develop new training program development SOP (feasibility study) - University | SDP | Objective dan Hasil Desk Research Training di University | Tersedianya SOP sebelum, saat, setelah pelaksanaan untuk menjalankan training program University serta feasibility study-nya. Deliverable: Document SOP Training di University Approver: BU Head + DIC | 2025-02-18 | 2025-03-14 | 25 | 0% | #REF! |  | -
1.4 | Identify new BPO solutions to be researched | RSE | List Target Industry (desk research) dari WBS 1.1 List Pertanyaan Menggali Informasi | Tersedianya solusi BPO yang siap untuk dijual ke market tujuan beserta dengan deck sederhana (masalah yang akan dihandle dan benefit solusi). Deliverable: Deck Solusi BPO (masalah industry, solusi product, daftar kompetitor Approver: BU Head + DIC | 2025-02-19 | 2025-04-30 | 71 | 0% | #REF! |  | -
1.5 | Implement industry knowledge training program | SDP | Target Industry yang telah di sepakati di Planning Cycle 2025 List materi pelatihan Mendapatkan expert di 2 industry | Terlaksananya training tentang industry yang menjadi target market. (Banking & University) Deliverable: Training Target Industry Knowledge Banking -> Winoto (IT HC BCA) Univesity -> DAW Approver: BU Head + DIC | 2025-02-18 | 2025-03-20 | 31 | 0% | #REF! |  | -
2 | ACE Brand & Market Elevate | DDD |  |  | 2025-02-03 | 2025-03-14 | 40 | 0% | #REF! |  | -
2.1 | Develop partnership package (individual and organization) | MTT | 1. Skema kerjasama eksisting 2. Skema kerjasama best practice | Tersedianya skema kerja sama pemasaran dengan individu dan juga organisasi untuk masing-masing produk. | 2025-02-28 | 2025-03-14 | 15 | 0% | #REF! |  | -
2.2 | Website revamp | ELA | 1. Vendor website development 2. Tersedianya logo terbaru untuk go live 3. Ekspektasi revamp 4. Budget untuk revamp | Tersedianya website dengan versi terbaru yang lebih informatif, user friendly, memenuhi ekspektasi dan kebutuhan ACE. | 2025-02-17 | 2025-03-07 | 19 | 0% | #REF! |  | -
2.3 | Develop socmed program | ELA | 1. Akun sosial media (IG, Tiktok, LinkedIn, Youtube) | Tersedianya social media dan content planning default setiap bulannya dan content calendar untuk bulan Maret. | 2025-02-03 | 2025-03-07 | 33 | 0% | #REF! |  | -
2.3.1 | [Sub-task] | [Name] |  |  |  |  | - | 0% | - |  | -
2.3.2 | [Sub-task] | [Name] |  |  |  |  | - | 0% | - |  | -
2.3.3 | [Sub-task] | [Name] |  |  |  |  | - | 0% | - |  | -
3 | ACE Process Excellence | YOC |  |  | 2025-02-19 | 2025-03-21 | 31 | 0% | #REF! |  | -
3.1 | Develop SOP for outsource management | MTT | Template SOP informasi proses existing | Tersedianya SOP pengelolaan karyawan outsource yang akan habis masa kontraknya. Deliverable: SOP Document Approver: BU Head (DDD) | 2025-02-19 | 2025-03-20 | 30 | 0% | #REF! |  | -
3.2 | Develop talent inventory data maintenance SOP | MTT | Template SOP informasi proses existing | Tersedianya SOP untuk maintain/manage database talent. Deliverable: SOP Document Approver: BU Head (DDD) | 2025-02-19 | 2025-03-20 | 30 | 0% | #REF! |  | -
3.3 | Review and improve channel incentive scheme | YOC | Skema perhitungan existing Target Improvement | Tersedianya skema insentif untuk mitra rekrutmen channel/organisasi. Deliverable: Dokumen Skema insentif Mitra Approver: BU Head (DDD) | 2025-02-19 | 2025-03-10 | 20 | 0% | #REF! |  | -
3.4 | Review and improve individual incentive scheme | YOC | Skema perhitungan existing Target Improvement | Tersedianya skema insentif untuk mitra rekrutmen individu. Deliverable: Dokumen Skema insentif Mitra Approver: BU Head (DDD) | 2025-02-19 | 2025-03-10 | 20 | 0% | #REF! |  | -
3.5 | Implement engagement event model for recruitment partners | DAN | List Schedule Mitra | Terlaksana kegiatan engagement dengan mitra rekrutmen. | 2025-02-19 | 2025-03-10 | 20 | 0% | #REF! |  | -
3.5.1 | Develop engagement event model for recruitment partners | [Name] |  |  |  |  | - | 0% | - |  | -
3.6 | Review and improve trainer recruitment SOP | MJU | Template SOP informasi proses existing | Tersedianya SOP untuk merekrut trainer. Deliverable: SOP Document Approver: BU Head (DDD) | 2025-02-19 | 2025-03-20 | 30 | 0% | #REF! |  | -
3.7 | Review and improve training SOP | SDP | Template SOP informasi proses existing | Tersedianya SOP dan panduan proses pelaksaan training. Deliverable: SOP Document Approver: BU Head (DDD) | 2025-02-19 | 2025-03-20 | 30 | 0% | #REF! |  | -
3.8 | Develop competency matrix for outsource talent | HMU | Performance appraisal karyawan outsource Kriteria High Quality Talent | Tersedianya matrix competency high quality talent. | 2025-02-19 | 2025-03-21 | 31 | 0% | #REF! |  | -
3.9 | Design and develop individual outsource talent development program | YOC | 3.8 Competency matrix for outsource talent | Tersedia rencana pengembangan karyawan outsource yang masuk kategori high quality talent. | 2025-02-19 | 2025-03-21 | 31 | 0% | #REF! |  | -
3.10 | Implement R&C program for employee | SDP | Skema best practice dalam melakukan R&C | Tersedianya skema reward & consequences untuk karyawan internal ACE. | 2025-02-19 | 2025-03-20 | 30 | 0% | #REF! |  | -
3.11 | Relevant training for employee | ADF | Materi Training yg akan diikuti List Karyawan yang perlu di training Jadwal training | Terlaksananya training untuk karyawan internal ACE. | 2025-02-19 | 2025-03-20 | 30 | 0% | #REF! |  | -
4 | ACE Digital Enablement | AFA |  |  | 2025-02-18 | 2025-04-30 | 72 | 0% | #REF! |  | -
4.1 | Develop sales and marketing tools (catalogue and testimonial) | DAN | - Data talent inventory sudah tervalidasi. - List sasaran user/client untuk diminta testimonial | Tersedianya sales deck versi terbaru dengan katalog posisi talent IT yang dimiliki saat ini di database dan testimoni dari user/client terhadap karyawan outsource ACE. Deliverable: Catalog Sales Deck Approval: DDD | 2025-03-14 | 2025-03-28 | 15 | 0% | #REF! |  | -
4.2 | Explore digital marketing for recruitment | ELA | - 2.2 Website ACE terbaru go live. - ekspektasi form apply | Tersedianya data riset ( harga ads, ads yang dipakai oleh competitor, reach masing masing ads or platform, dan data lain) dan dapat digunakan sebagai informasi untuk decision making, serta tersedianya platform/form untuk apply. Deliverable: Form Apply Job, Report Riset Platform dan rekomendasi Approval: DDD | 2025-03-07 | 2025-03-20 | 14 | 0% | #REF! |  | -
4.3 | Develop event booth for candidates recruitment | DAN | - Hasil Desk Research - ekspektasi hasil flyer, banner, booth - 2.2 Website ACE terbaru go live | Tersedianya supporting tools yang akan digunakan untuk proses event (form apply, booth, banner, flyer) Deliverable: QR Code, Booth, Flyer dan Banner template, Approval: DDD | 2025-03-07 | 2025-03-28 | 22 | 0% | #REF! |  | -
4.4 | Develop talent inventory management tools | AFA | Requirement ATS | Tersedianya roadmap development ATS. Deliverable: feature yang ada roadmap ATS Approval: DDD | 2025-03-05 | 2025-03-18 | 14 | 0% | #REF! |  | -
4.5 | AI automation for Talent Recruitment & Management | RAY | - list process all product - vendor untuk handle AI - proposal vendor - budget vendor - ekspektasi dampak penggunaan AI | Terimplementasi AI pada internal proses talent recruitment & management. Deliverable: Project Implementation Monitoring, report before after setelah AI, list result AI ( based on test case ) Approval: DDD | 2025-02-18 | 2025-04-30 | 72 | 0% | #REF! |  | -
4.6 | Develop task management application for recruitment partners | DSW | Website Mitra tersedia Alur proses baru untuk revamp dan ERD terbentuk 4.4 talent inventory management tools sudah ready 3.3 Skema Incentive Mitra 3.4 Skema Incentive Channel | Revamp aplikasi mitra dapat memfasilitasi baik ( pelamar, mitra rekrutmen individual dan channel). Deliverable: Website Mitra & Channels, feature baru di website Approval: DDD | 2025-02-18 | 2025-03-28 | 39 | 0% | #REF! |  | -
Template copy WBS
0 | [Nama Program Kerja] |  |  |  |  | - | - | 0% | - |  | -
0.1 | [Nama SI/Task] | [Name] |  |  |  |  | - | 0% | - |  | -
0.2 | [Nama SI/Task] | [Name] |  |  |  |  | - | 0% | - |  | -
0.2.1 | [Sub-task] | [Name] |  |  |  |  | - | 0% | - |  | -
0.2.2 | [Sub-task] | [Name] |  |  |  |  | - | 0% | - |  | -
0.2.2.1 | [Sub-task level 2] | [Name] |  |  |  |  | - | 0% | - |  | -
0.2.2.2 | [Sub-task level 2] | [Name] |  |  |  |  | - | 0% | - |  | -
0.2.2.2.1 | [Sub-task level 3] | [Name] |  |  |  |  | - | 0% | - |  | -
0.2.2.2.2 | [Sub-task level 3] | [Name] |  |  |  |  | - | 0% | - |  | -
Guide Prerequisite dan Definition of Done (DoD) → Meningkatkan probabilitas keberhasilan project.

## GanttChart BUP280225 (hidden)
| Project Start Date : | [8 empty] | Display Week
| 2025-01-02 | [8 empty] | 6 |  | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15
[12 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07
 | time axis 2025-02-03 to 2025-04-13
WBS | TASK | PIC | Prerequisite | Definition of Done | START | END | DAYS | % DONE | WORK DAYS | ACTUAL END | DELAY | time axis 2025-02-03 to 2025-04-13
1 | ACE New Expansion | MEG |  |  | 2025-02-18 | 2025-04-30 | 72 | 20% | #REF! |  | -
1.1 | Determine industry profile requirement | LLE | BMC, PASTLE, Porter 5 Forces, SWOT untuk Recruitment, Training dan BPO | Tersedianya profile industry dari target market yang akan dipenetrasi. Money: average budget, growth, revenue Authority: decision maker, influencer, entry point Needs: what, quantity, why, when Deliverable: - Report Industry Profile (Desk Research) - Validasi by sales terkait desk research yang dilakukan Approver: Scope pekerjaan -> DIC | 2025-02-19 | 2025-04-25 | 66 | 20% | #REF! |  | -
1.2 | Develop new training program development SOP (feasibility study) - CONFINS | RAG | Objective dan Materi Training CONFINS | Tersedianya SOP sebelum, saat, setelah pelaksanaan untuk menjalankan training program CONFINS serta feasibility study-nya. Deliverable: Document SOP Training ACE x CONFINS Approver: BU Head + DIC | 2025-02-18 | 2025-04-25 | 67 | 25% | #REF! |  | -
1.3 | Develop new training program development SOP (feasibility study) - University | SDP | Objective dan Hasil Desk Research Training di University | Tersedianya SOP sebelum, saat, setelah pelaksanaan untuk menjalankan training program University serta feasibility study-nya. Deliverable: Document SOP Training di University Approver: BU Head + DIC | 2025-02-18 | 2025-04-25 | 67 | 25% | #REF! |  | -
1.4 | Identify new BPO solutions to be researched | RSE | List Target Industry (desk research) dari WBS 1.1 List Pertanyaan Menggali Informasi | Tersedianya solusi BPO yang siap untuk dijual ke market tujuan beserta dengan deck sederhana (masalah yang akan dihandle dan benefit solusi). Deliverable: Deck Solusi BPO (masalah industry, solusi product, daftar kompetitor Approver: BU Head + DIC | 2025-02-19 | 2025-04-30 | 71 | 5% | #REF! |  | -
1.5 | Implement industry knowledge training program | SDP | Target Industry yang telah di sepakati di Planning Cycle 2025 List materi pelatihan Mendapatkan expert di 2 industry | Terlaksananya training tentang industry yang menjadi target market. (Banking & University) Deliverable: Training Target Industry Knowledge Banking -> Winoto (IT HC BCA) Univesity -> DAW Approver: BU Head + DIC | 2025-02-18 | 2025-03-20 | 31 | 25% | #REF! |  | -
2 | ACE Brand & Market Elevate | DDD |  |  | 2025-02-03 | 2025-03-07 | 33 | 45% | #REF! |  | -
2.1 | Develop partnership package (individual and organization) | MTT | 1. Skema kerjasama eksisting 2. Skema kerjasama best practice | Tersedianya skema kerja sama pemasaran dengan individu dan juga organisasi untuk masing-masing produk. | 2025-02-03 | 2025-02-21 | 19 | 25% | #REF! |  | -
2.2 | Website revamp | ELA | 1. Vendor website development 2. Tersedianya logo terbaru untuk go live 3. Ekspektasi revamp 4. Budget untuk revamp | Tersedianya website dengan versi terbaru yang lebih informatif, user friendly, memenuhi ekspektasi dan kebutuhan ACE. | 2025-02-17 | 2025-03-07 | 19 | 20% | #REF! |  | -
2.3 | Develop socmed program | ELA | 1. Akun sosial media (IG, Tiktok, LinkedIn, Youtube) | Tersedianya social media dan content planning default setiap bulannya dan content calendar untuk bulan Maret. | 2025-02-03 | 2025-03-07 | 33 | 90% | #REF! |  | -
2.3.1 | [Sub-task] | [Name] |  |  |  |  | - | 0% | - |  | -
2.3.2 | [Sub-task] | [Name] |  |  |  |  | - | 0% | - |  | -
2.3.3 | [Sub-task] | [Name] |  |  |  |  | - | 0% | - |  | -
3 | ACE Process Excellence | YOC |  |  | 2025-02-19 | 2025-06-30 | 132 | 29.17% | #REF! |  | -
3.1 | Develop SOP for outsource management | MTT | Template SOP informasi proses existing | Tersedianya SOP pengelolaan karyawan outsource yang akan habis masa kontraknya. Deliverable: SOP Document Approver: BU Head (DDD) | 2025-02-19 | 2025-03-20 | 30 | 30% | #REF! |  | -
3.2 | Develop talent inventory data maintenance SOP | MTT | Template SOP informasi proses existing | Tersedianya SOP untuk maintain/manage database talent. Deliverable: SOP Document Approver: BU Head (DDD) | 2025-02-19 | 2025-03-20 | 30 | 30% | #REF! |  | -
3.3 | Review and improve channel incentive scheme | YOC | Skema perhitungan existing Target Improvement | Tersedianya skema insentif untuk mitra rekrutmen channel/organisasi. Deliverable: Dokumen Skema insentif Mitra Approver: BU Head (DDD) | 2025-02-19 | 2025-03-10 | 20 | 50% | #REF! |  | -
3.4 | Review and improve individual incentive scheme | YOC | Skema perhitungan existing Target Improvement | Tersedianya skema insentif untuk mitra rekrutmen individu. Deliverable: Dokumen Skema insentif Mitra Approver: BU Head (DDD) | 2025-02-19 | 2025-03-10 | 20 | 50% | #REF! |  | -
3.5 | Implement engagement event model for recruitment partners | DAN | List Schedule Mitra | Terlaksana kegiatan engagement dengan mitra rekrutmen. Deliverable: Selesainya schedule Kegiatan engegament Mitra ACE dan terlaksananya kegiatan. Approver: BU Head (DDD) | 2025-05-01 | 2025-06-30 | 61 | 0% | #REF! |  | -
3.5.1 | Develop engagement event model for recruitment partners | [Name] |  | Deliverable: Schedule kegiatan dan model kegiatan Approver: BU Head (DDD) | 2025-02-19 | 2025-03-10 | 20 | 40% | #REF! |  | -
3.6 | Review and improve trainer recruitment SOP | MJU | Template SOP informasi proses existing | Tersedianya SOP untuk merekrut trainer. Deliverable: SOP Document Approver: BU Head (DDD) | 2025-02-19 | 2025-03-20 | 30 | 40% | #REF! |  | -
3.7 | Review and improve training SOP | SDP | Template SOP informasi proses existing | Tersedianya SOP dan panduan proses pelaksaan training. Deliverable: SOP Document Approver: BU Head (DDD) | 2025-02-19 | 2025-03-20 | 30 | 40% | #REF! |  | -
3.8 | Develop competency matrix for outsource talent | HMU | Performance appraisal karyawan outsource Kriteria High Quality Talent | Tersedianya matrix competency high quality talent. Deliverable: Dokumen Matrix Competency High Quality Approver: BU Head (DDD) | 2025-02-19 | 2025-04-11 | 52 | 30% | #REF! |  | -
3.9 | Design and develop individual outsource talent development program | YOC | 3.8 Competency matrix for outsource talent | Tersedia rencana pengembangan karyawan outsource yang masuk kategori high quality talent. Deliverable: kertas kerja pengembangan Talent Approver: BU Head (DDD) | 2025-02-19 | 2025-04-30 | 71 | 10% | #REF! |  | -
3.10 | Implement R&C program for employee | SDP | Skema best practice dalam melakukan R&C | Tersedianya skema reward & consequences untuk karyawan internal ACE. Deliverable: Dokumen Skema R & C ACE Approver: BU Head (DDD) | 2025-02-19 | 2025-03-20 | 30 | 5% | #REF! |  | -
3.11 | Relevant training for employee | ADF | Materi Training yg akan diikuti List Karyawan yang perlu di training Jadwal training | Terlaksananya training untuk karyawan internal ACE. Deliverable: Dokumen Schedule kegiatan Training karyawan internal Approver: BU Head (DDD) | 2025-02-19 | 2025-03-20 | 30 | 25% | #REF! |  | -
4 | ACE Digital Enablement | AFA |  |  | 2025-01-02 | 2025-03-28 | 86 | 4.167% | #REF! |  | -
4.1 | Develop sales and marketing tools (catalogue and testimonial) | DAN | - Data talent inventory sudah tervalidasi. - List sasaran user/client untuk diminta testimonial | Tersedianya sales deck versi terbaru dengan katalog posisi talent IT yang dimiliki saat ini di database dan testimoni dari user/client terhadap karyawan outsource ACE. Deliverable: Catalog Sales Deck Approval: DDD | 2025-03-14 | 2025-03-28 | 15 | 0% | #REF! |  | -
4.2 | Explore digital marketing for recruitment | ELA | - 2.2 Website ACE terbaru go live. - ekspektasi form apply | Tersedianya data riset ( harga ads, ads yang dipakai oleh competitor, reach masing masing ads or platform, dan data lain) dan dapat digunakan sebagai informasi untuk decision making, serta tersedianya platform/form untuk apply. Deliverable: Form Apply Job, Report Riset Platform dan rekomendasi Approval: DDD | 2025-03-07 | 2025-03-20 | 14 | 0% | #REF! |  | -
4.3 | Develop event booth for candidates recruitment | DAN | - Hasil Desk Research - ekspektasi hasil flyer, banner, booth - 2.2 Website ACE terbaru go live | Tersedianya supporting tools yang akan digunakan untuk proses event (form apply, booth, banner, flyer) Deliverable: QR Code, Booth, Flyer dan Banner template, Approval: DDD | 2025-03-07 | 2025-03-28 | 22 | 0% | #REF! |  | -
4.4 | Develop talent inventory management tools | AFA | Requirement ATS | Tersedianya roadmap development ATS. Deliverable: feature yang ada roadmap ATS Approval: DDD | 2025-01-02 | 2025-03-18 | 76 | 0% | #REF! |  | -
4.5 | AI automation for Talent Recruitment & Management | RAY | - list process all product - vendor untuk handle AI - proposal vendor - budget vendor - ekspektasi dampak penggunaan AI | Terimplementasi AI pada internal proses talent recruitment & management. Deliverable: Project Implementation Monitoring, report before after setelah AI Approval: DDD | 2025-02-18 | 2025-03-28 | 39 | 0% | #REF! |  | -
4.6 | Develop task management application for recruitment partners | DSW | Website Mitra tersedia Alur proses baru untuk revamp dan ERD terbentuk 4.4 talent inventory management tools sudah ready 3.3 Skema Incentive Mitra 3.4 Skema Incentive Channel | Revamp aplikasi mitra dapat memfasilitasi baik ( pelamar, mitra rekrutmen individual dan channel). Deliverable: Website Mitra & Channels, feature baru di website Approval: DDD | 2025-02-18 | 2025-03-28 | 39 | 25% | #REF! |  | -
Template copy WBS
0 | [Nama Program Kerja] |  |  |  |  | - | - | 0% | - |  | -
0.1 | [Nama SI/Task] | [Name] |  |  |  |  | - | 0% | - |  | -
0.2 | [Nama SI/Task] | [Name] |  |  |  |  | - | 0% | - |  | -
0.2.1 | [Sub-task] | [Name] |  |  |  |  | - | 0% | - |  | -
0.2.2 | [Sub-task] | [Name] |  |  |  |  | - | 0% | - |  | -
Guide Prerequisite dan Definition of Done (DoD) → Meningkatkan probabilitas keberhasilan project.